## Roster
Agency | Here | Name | Role | POC to Other Positions, Projects, Programs
USFWS | X | Bailey, Andrew | Alternate/Advisor/Past Chair | Fire Planning, Fire Danger, INFORM Fuels GIS
USFS |  | Beauchaine, Tony | *Primary/Chair | GCMU
USBR |  | Bell, Erin | Associate Member
USFS |  | Belongie, Cole | Advisor | EGP
USFS |  | Bowne, Elise | Alternate | IRIN, NIROPS
BIA | X | Chee, Jayvion | Alternate
Fire Research |  | Dillon, Greg | Associate Member
NPS |  | Edel, Skip | Alternate/Advisor/Past Chair | NIFS, DMC Liaison
USBR | X | Feizollahi, Ceema | Associate Member
DOI OWF |  | Hannemann, Don | Advisor | OWF/Wildland Fire Management Data /DMP
NPS | X | Hansen, Kathie | Alternate, GCMU Chair | UASD, UASM, WFLP
DOI |  | Harbo, Emmy | Advisor | DSTS/DMP
BIA | X | Kafka, Joe | *Primary Member/Past Chair
NWS |  | Kahler, Chad | Associate Member
Western States (Cal Fire) | X | Lim, Roberta | *Primary Member | CalFire/FIRESCOPE
WFMRDA |  | McClendon, Susan | *Primary Member | WFDSS, IFTDSS
BLM | X | Osterkamp, Julie | *Primary Member | InFORM, FRSC
BLM |  | Panunto Matt | Alternate
DOI OWF |  | Pederson, Roshelle | Parent Committee (DMC) Chair | DMC
Eastern States |  | Ramsey, Rebecca | *Primary Member | GISS
WFMRDA |  | Rumsey, Amanda | Alternate | WFDSS, IFTDSS
NASA |  | Shuman, Jackie | Associate Member
USFS |  | Sorenson, Kat | Associate Member | IRIN
Eastern States |  | Stripling, Curt | Associate Member | Texas FS
OWF |  | Thompson, Craig | Associate Member | DOI UAS, FRSC, DOIRSWG
USFWS |  | Tongier, Cameron | *Primary Member/Past Chair | SITL, FOBS, PSC2
WFMRDA | X | Vaughan, Jonah | Alternate | WFDSS, IFTDSS, FTEM, FMSF
*Indicates Voting Member

## Active Projects
Topic | Item | Accountability | Priority | Deadline | Status/Notes | URL References | URL References 2
Other Topics | Admin/Agenda for Spring Meeting | Tony |  |  | In-Person Meeting Agenda Topics Kat/Elise GSC Rep for IRIN/443 Course | Draft Agenda Spring Meeting
| Bylaws | Tony |  |  | Please make comments to the draft Bylaws by the Annual Meeting. | 2025 Draft Bylaws | 2019 Bylaws
| IPTM | Tony |  |  | IPTM was a big focus of the NWCG Annual Meeting. GISS and IRIN are slated for early 2026. | Decision Workflow | Decision Workflow Roles and Responsibilities
| IFPRS Data Advisory Group | Cameron
| FTEM dashboard / IFPRS Treatment in FTEM | Amanda |  |  |  | Dashboard - https://nifc.maps.arcgis.com/apps/dashboards/98de26c0239649858df20c1c9536676d comment form - https://forms.office.com/pages/responsepage.aspx?id=4F2CSwVwPUuaFHhBHyhmAxOzMCzJHVJIkKgK6BVxypRUQzY4TEtHNEpHWUI0NExPTjg3NFBMN09NUCQlQCN0PWcu | FTEM - Adding Treatments Using the Buffer Area
| INFORM updates | Julie |  |  |  | Merged Perimeters Production - Overview
Data Standards | Spatial Fire Planning | Susan |  |  |  | https://isfps-nifc.hub.arcgis.com
| Fuels Treatment/Fuels Advisory Group | Amanda
| Fire Danger Rating Area | Andrew |  |  | Kick off mtg 2 weeks ago, trying to determine scope. Would like more dispatch experience in group. Trying to meet every 2 weeks.
GISS Position | Geospatial Curriculum Management Unit (GCMU) | Kathie |  |  | GeoOps (PMS 926) and GISS Workflow (PMS 936-1) updates made for 2025. Several map standard in GeoOps were updated and some new map standards were created. Situation Unit Map has been depricated. There is a statement in GeoOps on teh Map Product Standards page that says the Operations map should be used as an acceptable substitution for task book purposes. PununTools was updated to reflect the map standard changes. It includes a way to add 'suggested' definition queries for Event data for each map standard in the Incident Setup ArcGIS Pro tool.
| S-341 and RT-341 | Kathie |  |  | Still fairly busy with RT-341 map grading. Deadline for maintaining NIFC Org role has passed so all completions now are manual to get access to the NIFC org. S-341 Session 2 started Monday and week 1 wraps up today. We have 60 students in the course and it looks like everyone will pass this week and move on to Week 2.
| S-441 | Kathie/Tony |  |  | Still on hold | NWCG EB Memo 24-006
IRIN Position | (IRIN Steering Committee) | Elise |  |  | Spring refresher for IRIN and IRIN(T)s just completed. Three half-days, covering both workflow, new request/closeout/log process, and agreed upon data standardization. New taskbook is nearly ready for GSC review, hoping to have it in time for the in-person meeting at the end of the month. New mirrors installed on one Phoenix scanner, other scanner is in progress. QA/QC testing still scheduled for this month.
| S-443 | Elise |  |  | No class this spring (every other year). Working on updating the IRIN PTB. NIROPS requests have moved to IAA.
Projects and Applications | Open Data site | Skip |  |  |  | IMSR Incident Locations View: Current ¦ IMSR Incident Locations View: Current ¦ National Interagency Fire Center (arcgis.com)
| Boundary layer update GACC, Dispatch, Initial Attack Frequency Zones, and Jurisdictional Boundary. | Emmy |  |  | New cartographic Jurisdictional Units product now available as well - census block group backfill was removed and all units depicted as multipart, so the layer depicts unit boundary extent. Designed for the FTEM dashboard but other dashboarding folks might want it as well | https://firenet365.sharepoint.com/:b:/r/sites/NWCG_Geospatial_SubCommittee/Shared%20Documents/General/Projects%20-%20ACTIVE/Wildland%20Fire%20National%20Dataset%20Update%20Workflow-1.pdf?csf=1&web=1&e=Ifo8Is | Jurisdictional Units - Cartographic Products
| Fire History Dataset (Point/Polygon) Data Management Strategy | Susan |  |  |  | https://teams.microsoft.com/l/file/393C0D1F-F2B3-468F-8092-ECFBF9CECC70?tenantId=4b825de0-7005-4b3d-9a14-78411f286603&fileType=docx&objectUrl=https%3A%2F%2Ffirenet365.sharepoint.com%2Fsites%2FNWCG_Geospatial_SubCommittee%2FShared%20Documents%2FGeneral%2FProjects%20-%20ACTIVE%2FFireHistoryDataMgmtPlan_EJH%2FNIFC%20Geospatial%20Historic%20Data%20Managment%20Plan_working_version1_August%202022.docx&baseUrl=https%3A%2F%2Ffirenet365.sharepoint.com%2Fsites%2FNWCG_Geospatial_SubCommittee&serviceName=teams&threadId=19:028833cdae2a4e8486f5791f97e36608@thread.skype&groupId=bdb4ef68-7605-4329-a6b3-b473dff01032
External Communication | NWCG Web Page(s) | Skip, Kathie, Tony
| ESRI Wildfire Community Group | Skip, Kathie |  |  |  | GeoNet Wildfire Response Page

## Bin Projects
Category | Item | Accountability | Priority | Deadline | Status / Notes | URL references
Data Standards | Protection Unit | Andrew |  |  | Waiting until FMU data standard before starting this effort. Domain list for Jurisdictional unit domain issue since it includes 'Private' and that is not a valid value. Move to BIN
GISS Position | working with UAS positions | Steve Levitt |  |  | Keep GSC updated on UAS work
External Communication | [5 empty] | GISS Position Page
Projects & Applications | WFDSS/IFTDSS/FTEM | WFMRDA |  | ongoing
| NIROPS | Elise
| INFORM | Dianna |  | ongoing
| EGP | Cole |  | ongoing
| other ICS positions |  |  | ongoing
Subgroups & Task Teams | GCMU | Kathie |  | NA | see active projects tab | 2019 GTU & S-341 cadre workshop agenda
DMC & GSC Peers | DMC | Skip |  | NA
| DSTS | Andrew |  | NA |  | DSTS folder
| Resource data from IROC |  |  |  | In Open data site
| FRSC | Dianna |  | NA

## Agency Round Robin
Round Robin Agency Updates | Reps | Notes | URL
USFS | Tony/Elise | Preparing for the new NSRS datums. getting ready for WFDSS next gen and Spatial Fire Planning Service
BLM | Julie/Matt | * pushing everyone to update to ArcGIS Pro 3.3.5 due to reported security vulnerabilities * created Human Fire Caused Dashboard (not specific to BLM, but for BLM), url to left * getting ready for WFDSS next gen and Spatial Fire Planning Service * ArcGIS API duplication issue: https://support.esri.com/en-us/bug/in-arcgis-api-for-python-23-and-24-a-query-on-a-referen-bug-000171499 | BLM Fire Cause Dashboard 2005 to 2024
BIA | Joe/Jayvion
NPS | Skip/Kathie | IFPRS/WFDSS NextGen prep
Western States | Roberta | Update to GISS taskbook
Eastern States | Rebecca/Curt | • Middle of our Spring Fire Seasons • Collecting answers to an informal survey I have posed to GIS counter parts in the Eastern States to find out information about their wildfire data workflow (help get a baseline of information about each state in the Eastern region and will write up a summary that can be utilized). • Current State Contacts 16 represented (3 Fire Compacts), missing 17 (3 more Fire Compacts) but email call is out for representatives
WFIT DMP/DMC | Don/Cole/Roshelle/Emmy | April Data Summit - Virtual - Registration now open, draft agenda posted | Data Summit: https://www.wildfire.gov/page/data-management-training-conferences-and-meetings
DOI OWF / FRSC | Julie | * FRSC nothing new, Merge capabilities in InFORM still hot topic. * Working on data integrity, domains in data fields, state uplaods into InFORM
FWS | Cameron/Andrew | Hired a new Analyst. Report date 4/21. Data preservation efforts, One Drive synching, Desktop Virtualization for Pro coming.
WFMRDA | Amanda/Susan/Jonah | WFDSS NextGen Launched 3/26 Weekly SFPS Office Hours Wednesday @ 1400 | https://isfps-nifc.hub.arcgis.com/
BOR | Ceema/Erin | Presentation from IFPRS and getting help on translating data