## Roster
Agency | Here | Name | Role | POC to Other Positions, Projects, Programs
USFWS | x | Bailey, Andrew | Alternate/Advisor/Past Chair | Fire Planning, Fire Danger, INFORM Fuels GIS
USFS | x | Beauchaine, Tony | *Primary/Chair | GCMU
USBR |  | Bell, Erin | Associate Member
USFS | x | Belongie, Cole | Parent Committee (DMC) Co-Chair | EGP
BIA | x | Chee, Jayvion | Alternate
NPS | x | Edel, Skip | Alternate/Advisor/Past Chair | NIFS, DMC Liaison
USBR | x | Feizollahi, Ceema | Associate Member
USFWS | x | Gromatzky, Kari | Advisor
DOI OWF | x | Hannemann, Don | Parent Committee (DMC) Co-Chair | OWF/Wildland Fire Management Data /DMP
NPS | x | Hansen, Kathie | Alternate, GCMU Chair | WFLP, UASD & UASM (Adam Ridley)
DOI | x | Harbo, Emmy | Advisor | DSTS/DMP
BIA | x | Kafka, Joe | *Primary Member/Past Chair
NWS |  | Kahler, Chad | Associate Member
Western States (Cal Fire) | x | Lim, Roberta | *Primary Member | CalFire/FIRESCOPE
WFMRDA | x | McClendon, Susan | *Primary Member | WFDSS, IFTDSS
BLM | x | Osterkamp, Julie | *Primary Member | InFORM, FRSC
BLM | x | Panunto, Matt | Vice-Chair
Eastern States | x | Ramsey, Rebecca | *Primary Member | GISS
WFMRDA |  | Rumsey, Amanda | Alternate | WFDSS, IFTDSS
USFS | x | Sorenson, Kat | Associate Member | IRIN
Eastern States |  | Stripling, Curt | Associate Member | Texas FS
USFWS | x | Tongier, Cameron | *Primary Member/Past Chair | SITL, FOBS, PSC2
WFMRDA |  | Vaughan, Jonah | Alternate | WFDSS, IFTDSS, SFPS
*Indicates Voting Member

## Active Projects
Topic | Item | Accountability | Priority | Deadline | Status/Notes | URL References | URL References 2 | URL References 3
| Agency Updates | All
Other Topics | Admin | Tony |  |  | AD Pay Plan for GISS - Heard back from IBC chair, they initially looked at the IPD pre-2022, will continue to work with them on additional documentation needed. Dates for Spring Meeting: Week of April 27th (28-30) Room reserved at NIFC | PD IPD Crosswalk
| NWCG Reorganization | Tony |  |  | Agency selections made. Final implementation Pushed back until July 1st, 2026 Annual Meeting in Boise, February 18-19. Chairs and Vice Chairs invited. | Final Committee Reorganization | FAQ's
| IPTM | Tony |  |  | IPTM workshop and GISS process being pushed back. Workshop dates TBD. Had planned on two groups of positions going through IPTM this spring, first group rescheduled to later in the spring. GISS is in the second group, no timeline yet. | Decision Workflow | Decision Workflow Roles and Responsibilities | EXAMPLE Incident Position Standards for UASD
| IPTM SMEs | Tony |  |  | Currently have 19 SMEs that have responded. Once we get word from NWCG we can make selections | SME Interest Signup Form
| WFIGS HVRAs | All
| IFPRS Data Advisory Group | Cameron |  |  | Progressive reporting is live! We just received the data dictionary/terminology/glossary updates from the developer to be reviewed by "end of january"
| Integrated Interagency Fuels Treatments and FTEM | Amanda/Jonah |  |  | No Updates | FTEM Dashboard: https://nifc.maps.arcgis.com/apps/dashboards/98de26c0239649858df20c1c9536676d | FTEM - Adding Treatments Using the Buffer Area
| INFORM updates | Julie |  |  | Morgan Pence now USFS InFORM Business lead (vice Laura Barrett). Sha has helped drastically with updating the InFORM Hub so now showing current issues (updated weekly), and working with devs to have normal schedule of version releases and communicating that out. | InFORM: Known Bugs ¦ InFORM Website
Data Standards | Spatial Fire Planning | Susan |  |  | Delay on new design due to personell issues. The existing services will be cleaned up (deletes) and back online hopefully early the week of 12/15. Please check WFDSS OFFICE HOURS Team channel for updates or reach out to Amanda or Susan for questions.Since we are making changes after use for one fire season, we will be updating the standard. Wes is sheperading that effort. | https://isfps-nifc.hub.arcgis.com
| Fuels Treatment/Fuels Advisory Group | Amanda |  |  | No Updates
| Organizational Kind/Category: Protection/Jurisdiction/Landowner | Tony/Emmy/Jonah |  |  | Complete. Out for NWCG Comments. See crosswalk from old Landowner Kind/Cat --> Organization Kind/Cat (NEW) | Org Kind/Cat Crosswalk (Old Standard --> New) | Org Kind/Cat Standard (NEW)
| Jurisdictional Units | Amanda/Emmy/Jonah |  |  | New 2.0 Standard finalized. Draft JU 2025 dataset complete and in QA review. Need to get better state data into PADUS. Use SMA with state data? Ask NASF reps to confirm use of SMA? Julie will check with BLM state leads. Emmy will create a briefing document to highlight issues and possible solutions. | JU Version 2
| Protection Units | Tony/Jonah |  |  | PU DS nearing completion. Aim to complete on 1/12. Plan for a New Schema Publish in January alongside JU. | Protecting Unit | Protection Schema Comparison
| Fire Danger Rating Area | Andrew |  |  | Need to invite these folks to our recurring Monday calls after PU is complete. Andrew sent email to FDRA group.
GISS Position | Geospatial Curriculum Management Unit (GCMU) | Kathie |  | 2026-02-01 | No new updates from GCMU. GeoOps and GISS Workflow updates pending. Web pages under review now based on 2026 NIFS updates. | NWCG Geographic Information Systems Specialist (GISS) Training page (WFLP)
| S-341 and RT-341 | Kathie |  |  | 2026 RT course opened on 1/2/26 at noon pacific. Please forward announcement to your agency email lists. 2026 S-341 course on schedule with confirmed students and cadre. Prework for session 1 will open up first week of February. | https://www.wildlandfirelearningportal.net/course/view.php?id=4061
| S-441 | Kathie/Tony |  |  | Confirmed with Dave that NWCG won't look at additional training until after IPTM. | NWCG EB Memo 24-006
IRIN Position | (IRIN Steering Committee) | Kat |  |  | NIROPS Closeout narrative made available on the IAA portal back in July, wasn't widely communicated. Maybe something can be added to RT. Kat plans to better communicate this this coming spring through her channels. Also producing a 'matrix' of the different platforms' sensitively and accuracy due around March 1st.
| S-443 | Kat |  |  | S-443 scheduled for april 20-24 at NTDP in Missoula, MT. as of today, 58 noms submitted for 30 seats. The cadre is set with Jennifer Frazier as lead instructor. | Draft PTB
Projects and Applications | Open Data site | Skip |  |  | Updates | IMSR Incident Locations View: Current ¦ IMSR Incident Locations View: Current ¦ National Interagency Fire Center (arcgis.com)
| Boundary layer update GACC, Dispatch, Initial Attack Frequency Zones, and Jurisdictional Boundary. | Emmy |  |  | October updates complete for IA Attack & Dispatch Boundaries. Taking edits at anytime. | https://firenet365.sharepoint.com/:b:/r/sites/NWCG_Geospatial_SubCommittee/Shared%20Documents/General/Projects%20-%20ACTIVE/Wildland%20Fire%20National%20Dataset%20Update%20Workflow-1.pdf?csf=1&web=1&e=Ifo8Is | Jurisdictional Units - Cartographic Products
| Fire History Dataset (Point/Polygon) Data Management Strategy | Susan |  |  | We plan to try and work on a dashboard for Fire Perimeters in Jan/Feb. Along with the update to the Interagency Fire Perimeter layer....that update will come from WFIGS this year exclusively. | https://teams.microsoft.com/l/file/393C0D1F-F2B3-468F-8092-ECFBF9CECC70?tenantId=4b825de0-7005-4b3d-9a14-78411f286603&fileType=docx&objectUrl=https%3A%2F%2Ffirenet365.sharepoint.com%2Fsites%2FNWCG_Geospatial_SubCommittee%2FShared%20Documents%2FGeneral%2FProjects%20-%20ACTIVE%2FFireHistoryDataMgmtPlan_EJH%2FNIFC%20Geospatial%20Historic%20Data%20Managment%20Plan_working_version1_August%202022.docx&baseUrl=https%3A%2F%2Ffirenet365.sharepoint.com%2Fsites%2FNWCG_Geospatial_SubCommittee&serviceName=teams&threadId=19:028833cdae2a4e8486f5791f97e36608@thread.skype&groupId=bdb4ef68-7605-4329-a6b3-b473dff01032
External Communication | NWCG Web Page(s) | Skip, Kathie, Tony |  |  | Nothing besides GeoOps/Workflow pages. Waiting for NWCG ReOrg.
| ESRI Wildfire Community Group | Skip, Kathie |  |  |  | ESRI Community Wildfire Response Page
Other

## Bin Projects
Category | Item | Accountability | Priority | Deadline | Status / Notes | URL references
GISS Position | working with UAS positions | Steve Levitt |  |  | Keep GSC updated on UAS work
External Communication | [5 empty] | GISS Position Page
Projects & Applications | WFDSS/IFTDSS/FTEM | WFMRDA |  | ongoing
| NIROPS | Elise
| INFORM | Dianna |  | ongoing
| EGP | Cole |  | ongoing
| other ICS positions |  |  | ongoing
Subgroups & Task Teams | GCMU | Kathie |  | NA | see active projects tab | 2019 GTU & S-341 cadre workshop agenda
DMC & GSC Peers | DMC | Skip |  | NA
| DSTS | Andrew |  | NA |  | DSTS folder
| Resource data from IROC |  |  |  | In Open data site
| FRSC | Dianna |  | NA

## Agency Round Robin
Round Robin Agency Updates | Reps | Notes | URL
USFS | Tony/Cole/Jonah/Kat | FS upgraded to Pro version 3.5.2. Potential issue with downloading an offline map when setting 'Ask where to save before downloading' option is selected. Tested this and it is not an issue with desktop installs. Field Maps and iOS26 issue signing in with eAuth - Official bug with Esri New licences for rental through SmartSource
BLM | Julie/Matt | BLM planning to make ArcGIS Pro v3.5.5 available for local instal sometime later part of January. No new information on WFS.
BIA | Joe/Jayvion
NPS | Skip/Kathie | Waiting to see where we end up in the new Wildland Fire Service.
Western States | Roberta | CA Federal IMTs down to from 10 this year.
Eastern States | Rebecca/Curt
WFIT DMP/DMC | Don/Cole//Emmy
FRSC | Julie | Fire data user guide getting 508 compliant this week. Finishing up accompaning demo videos on how to accurately calculate acreage and agency fire count utilizing the FODR. Moving focus to new 2025 Wildfire Statistics Report (from FODR data). | FireDataUserGuide DRAFT folder
FWS | Cameron/Andrew/Kari | Cam: Nothing of great interest to report Andrew: -FWS Version of ArcGIS Pro is now 3.5.5. FWS will begin removing older versions in a few months. -FWS is working on an FMP inventory which can be joined to make spatial data. Thanks Kari G! -FWS is working to make sure all FWS lands have WFDSS spatial data. -Andrew upgraded Advanced NFDRS extractor to new EGP FME Server. -Andrew will be working to upgrade NFDRS Apps in AGOL. -Andrew will be DOI rep for NWCG Planning Management Committee. Not likely to be like IFPC.
WFMRDA | Amanda/Susan/Jonah | WFDS in O&M, working on process to upload MTT and Farsite results. | https://isfps-nifc.hub.arcgis.com/
BOR | Ceema/Erin